## Slide 1
PCS WIRELESS
Customer Portal
Project Plan
Stage 1 Delivery — 5 Sprints · May to July 2026
Document Version
1.0
Date
May 7, 2026
Status
Draft — Pending Sign-Off
Prepared by
Development Team
5 Sprints — May to July 2026

## Slide 2
Delivery Timeline
May 18
Jun 1
Jun 15
Jun 29
Jul 13
Jul 24
Sprint 1
Auth · Navigation · Orders
Sprint 2
Shipments
Sprint 3
Financial Management
Sprint 4
Support Tickets
Sprint 5
Activity · Settings · Notifications
M0 Infrastructure Ready — May 29
M1 Auth + Orders Live — May 29
M2 Shipments Live — Jun 12
M3 Financial Live — Jun 26
M4 Support Live — Jul 10
M5 Stage 1 Complete — Jul 24

## Slide 3
Milestones
M0
Deploy pipelines and infrastructure ready
May 29, 2026
May 29, 2026
M1
Authentication and Order Management live — portal accessible to customers
May 29, 2026
May 29, 2026
M2
Shipment Tracking live
Jun 12, 2026
Jun 12, 2026
M3
Financial Management live
Jun 26, 2026
Jun 26, 2026
M4
Customer Support live
Jul 10, 2026
Jul 10, 2026
M5
Stage 1 complete — all features live
Jul 24, 2026
Jul 24, 2026

## Slide 4
Sprint 1 — Infrastructure, Authentication & Orders
May 18 – May 29, 2026
M0 & M1: May 29
Deploy Pipelines
• CI/CD pipeline (GitHub Actions → Render)
• Staging + production environments on Render
• PostgreSQL database provisioning
• Next.js 14 scaffold with Tailwind CSS
Authentication (US-01–04)
• Auth0 sign-in integration
• Password reset flow
• PCS staff credential provisioning
• Protected route middleware
Navigation & Global UI (US-67, 68, 70)
• Desktop sidebar navigation
• Mobile bottom tab bar + hamburger drawer
• Responsive layout (mobile & desktop)
Order Management (US-12–16)
• Order listing with status filter and search
• Order detail page with line items and shipping
• Order status timeline
Dashboard Additions
✓ Dashboard shell — landing page after login
✓ Open Orders KPI card

## Slide 5
Sprint 2 — Shipments
Jun 1 – Jun 12, 2026
M2: Jun 12
Shipment Tracking (US-20–24)
• Shipment listing page
• Status filter (In Transit, Delivered, Pickup Ready, Exception)
• Shipment detail with current status and last update
• Bill of Lading + Packing List download
Dashboard Additions
✓ Pending Shipments KPI card added to Dashboard

## Slide 6
Sprint 3 — Financial Management
Jun 15 – Jun 26, 2026
M3: Jun 26
Financial Management (US-30–38)
• Financial summary (outstanding, past due, credit limit, payment terms)
• Aging breakdown (Current, 30, 60, 90+ days)
• Invoice list + status filter (Open, Past Due, Paid)
• Invoice detail with line items and payment history
• Invoice PDF + account statement download
• Invoice dispute flow
• Payments list + detail view
• Credit memos list + detail view
Dashboard Additions
✓ Outstanding Balance KPI card added
✓ Past Due KPI card added
✓ Past-due invoice alert banner

## Slide 7
Sprint 4 — Support Tickets
Jun 29 – Jul 10, 2026
M4: Jul 10
Support Tickets (US-45–55)
• Create ticket (category, subject, description, priority, linked order)
• Ticket list with status + category filter
• Ticket detail with full conversation thread
• Reply to ticket + file attachment
• Assigned PCS team member display
• Ticket priority (Normal / Urgent)
• Order / Quote ID linking
• Post-resolution satisfaction rating
Dashboard Additions
✓ Open Support Tickets KPI card added
✓ Contact Support quick-action button

## Slide 8
Sprint 5 — Activity Log, Account Settings & Notifications
Jul 13 – Jul 24, 2026
M5: Jul 24 — Stage 1 Complete
Activity Log (US-40–44)
• Chronological account event log
• Category filter (Orders, Shipments, Payments, Support)
• Action-required flagging + record linking to related records
Account Settings (US-56–66)
• Company profile editing + tax certificate upload
• User management (invite, roles, activate/deactivate)
• Theme, regional settings, notification preferences
• Password change, 2FA, active session management
Notifications (US-71–73)
• Email + SMS notification preferences
• In-app notification bell + alert panel
Dashboard Additions
✓ Recent activity feed added to Dashboard
✓ Notification bell in portal header